## Migration Command Center
SQL SERVER 2016 → 2025
ENTERPRISE MIGRATION PLAYBOOK ¦ ASSESS • BUILD • MIGRATE • CUT OVER • STABILIZE
PROJECT COMMAND CENTER
TOTAL CHECKPOINTS |  | COMPLETED |  | IN PROGRESS | BLOCKED
MIGRATION PHASES
Phase | Objective | Gate / Exit Criteria | Owner | Status
01 ¦ Assess | Understand workload, dependencies and risk | Assessment reviewed; test scope agreed | DBA Lead | Not Started
02 ¦ Build | Provision and validate SQL 2025 HA infrastructure | Cluster, AG listener and failover tests pass | Infra / DBA | Not Started
03 ¦ Prepare | Seed databases, configure log shipping and migrate metadata | Log shipping stable; restore sequence validated | DBA Team | Not Started
04 ¦ Cut Over | Execute controlled production transition | Go/No-Go approved; app checks pass | Change Lead | Not Started
05 ¦ Stabilize | Monitor, tune, secure and validate recovery | Monitoring, backups and handover accepted | DBA / App Owner | Not Started
HOW TO USE
Use the Master Checklist as the single source of truth. Assign owners and target dates, update status during each checkpoint, and record evidence or change-ticket references. This workbook is a planning template—not a substitute for environment-specific testing, an approved change plan, or a tested rollback procedure.

## Master Checklist
ID | Phase | Workstream | Task / Checkpoint | Suggested Owner | Timing | Evidence / Exit Criteria | Status | Priority | Target Date | Actual Date | Evidence / Ticket / Notes
MIG-001 | 01 ¦ Assess | Governance | Confirm source/target instances, databases, business criticality, owners and scope. | DBA Lead | Before assessment | Approved scope document | Not Started | High
MIG-002 | 01 ¦ Assess | Support & upgrade path | Confirm SQL Server versions/editions, OS support, licensing and target build compatibility. | DBA Lead / Infra | Before build | Compatibility and licensing sign-off | Not Started | High
MIG-003 | 01 ¦ Assess | Inventory & dependencies | Inventory databases, sizes, jobs, logins, linked servers, SSIS, reports, app connections and dependencies. | DBA Team | Assessment | Reviewed dependency inventory | Not Started | High
MIG-004 | 01 ¦ Assess | Upgrade assessment | Review deprecated features, breaking changes, known issues and remediation actions. | DBA Team | Assessment | Findings assigned and tracked | Not Started | High
MIG-005 | 01 ¦ Assess | Compatibility-level baseline | Record current compatibility levels; define candidate databases for controlled level 170 testing. | DBA Team | Assessment | Baseline captured; no unapproved production change | Not Started | High
MIG-006 | 01 ¦ Assess | Workload baseline | Capture CPU, memory, I/O latency, waits, PLE, top queries and Query Store data where available. | DBA / Monitoring | Before testing | Baseline window and metrics saved | Not Started | High
MIG-007 | 01 ¦ Assess | Application validation plan | Define critical transactions, integrations, batch windows, acceptance criteria and test owners. | App Owner / QC | Assessment | Test plan signed off | Not Started | High
MIG-008 | 01 ¦ Assess | Backup & recovery review | Verify full/differential/log policies, retention, restore tests, RPO/RTO and rollback requirements. | DBA Lead | Assessment | Recovery strategy reviewed and tested | Not Started | Critical
MIG-009 | 01 ¦ Assess | Risk & change plan | Document outage estimate, dependencies, communications, approvals and go/no-go authority. | Change Lead | Before change | Approved change and risk register | Not Started | High
MIG-010 | 01 ¦ Assess | Non-production validation | Restore representative databases and validate application/workload scenarios. | DBA / App / QC | Testing | Test results reviewed and signed off | Not Started | High
MIG-011 | 02 ¦ Build | Provision destination VMs | Provision SQLDB3/SQLDB4 or environment-specific names with approved sizing and networking. | Cloud / Infra | Before migration | Build and sizing approved | Not Started | High
MIG-012 | 02 ¦ Build | Storage layout & capacity | Validate data/log/TempDB volumes, throughput, latency, free space and growth headroom. | Infra / DBA | Before SQL install | Storage tests and capacity sign-off | Not Started | High
MIG-013 | 02 ¦ Build | OS security baseline | Apply approved patches, hardening, service accounts, firewall rules and endpoint exclusions as permitted. | Windows / Security | Before SQL install | Security baseline met | Not Started | High
MIG-014 | 02 ¦ Build | Windows Failover Cluster | Join nodes, validate networking/quorum and configure Cloud Witness where appropriate. | Windows / Cloud | Before AG | Cluster validation report reviewed | Not Started | High
MIG-015 | 02 ¦ Build | Install SQL Server 2025 | Install approved edition/build, updates, service accounts, directories and startup settings. | DBA / Infra | After cluster | Build recorded; installation checks pass | Not Started | Critical
MIG-016 | 02 ¦ Build | Instance configuration | Review max server memory, MAXDOP, cost threshold, TempDB and approved configuration settings. | DBA Lead | After install | Configuration baseline approved | Not Started | High
MIG-017 | 02 ¦ Build | Enable Always On | Validate endpoint, permissions, firewall and replica connectivity. | DBA Team | After install | Replica connectivity verified | Not Started | Critical
MIG-018 | 02 ¦ Build | Create destination AG | Configure AG/listener, availability mode, failover and health detection to meet design. | DBA Team | Before seed | Design and failover mode validated | Not Started | Critical
MIG-019 | 02 ¦ Build | Azure Load Balancer / listener | Configure supported load balancer rules/probe and listener networking per Azure architecture. | Cloud / Network | Before testing | Listener resolves and routes correctly | Not Started | High
MIG-020 | 02 ¦ Build | HA and failure testing | Test planned failover and controlled node interruption; verify client reconnect and app behavior. | DBA / App / Infra | Before migration | Failover evidence approved | Not Started | Critical
MIG-021 | 03 ¦ Prepare | Confirm FULL recovery model | Confirm each database uses FULL recovery and required log backups are running. | DBA Team | 3–4 days before cutover | Recovery model and backup chain verified | Not Started | Critical
MIG-022 | 03 ¦ Prepare | Coordinate existing log backup jobs | Review schedules, destinations, retention and cleanup; avoid conflicting file handling. | DBA Team | Before log shipping | Backup ownership and file handling documented | Not Started | Critical
MIG-023 | 03 ¦ Prepare | Seed full backups | Take compressed/checksum-enabled full backups; verify completion and accessibility. | DBA Team | Before log shipping | Backup verified and accessible | Not Started | Critical
MIG-024 | 03 ¦ Prepare | Restore seed to SQLDB3 | Restore full backup using NORECOVERY and map target data/log paths. | DBA Team | Before log shipping | Database remains RESTORING | Not Started | Critical
MIG-025 | 03 ¦ Prepare | Restore seed to SQLDB4 | Restore matching full backup using NORECOVERY; validate target-specific file paths. | DBA Team | Before log shipping | Database remains RESTORING | Not Started | Critical
MIG-026 | 03 ¦ Prepare | Configure log shipping | Configure source backup and secondary restore jobs, schedules, shared paths and monitoring. | DBA Team | Before cutover | Backup/restore jobs complete successfully | Not Started | Critical
MIG-027 | 03 ¦ Prepare | Validate log shipping sequence | Compare matching backup/restore history; confirm required logs restore in sequence and monitor lag. | DBA Team | Until cutover | No unexplained gaps; lag within threshold | Not Started | Critical
MIG-028 | 03 ¦ Prepare | Configure alerts | Validate log shipping alert job, thresholds, Database Mail and DBA notification delivery. | DBA / Monitoring | After setup | Test alert received | Not Started | High
MIG-029 | 03 ¦ Prepare | Migrate logins & permissions | Script logins/SIDs and permissions; decide instance vs Contained AG scope. | DBA Team | Before cutover | Access tests passed; ownership confirmed | Not Started | High
MIG-030 | 03 ¦ Prepare | Migrate SQL Agent jobs & objects | Script jobs, operators, linked servers, audits, Extended Events and maintenance plans. | DBA Team | Before cutover | Objects reviewed; jobs not prematurely enabled | Not Started | High
MIG-031 | 03 ¦ Prepare | Pre-cutover rehearsal | Rehearse steps, time tasks, validate evidence capture and test rollback/decision points. | Change Lead / DBA | Before change | Rehearsal completed; runbook approved | Not Started | Critical
MIG-032 | 04 ¦ Cut Over | Change bridge & approvals | Confirm change approval, outage window, stakeholders, backups, contacts and decision authority. | Change Lead | Cutover start | Approvals recorded | Not Started | Critical
MIG-033 | 04 ¦ Cut Over | Stop application writes | Quiesce application/background writers; verify no process can modify source. | App Owner / DBA | Cutover | Write freeze confirmed | Not Started | Critical
MIG-034 | 04 ¦ Cut Over | Drain pending log shipping | Verify required transaction log backups restored on both destinations. | DBA | Cutover | Destination restore sequence verified | Not Started | Critical
MIG-035 | 04 ¦ Cut Over | Remove source database from AG | Perform source AG removal only per approved runbook and verified prerequisites. | DBA Lead | Cutover | Source AG state documented | Not Started | High
MIG-036 | 04 ¦ Cut Over | Take final tail-log backup | Take tail-log backup WITH NORECOVERY after writes stop and prerequisites are confirmed. | DBA Team | Cutover | Tail-log backup completed and verified | Not Started | Critical
MIG-037 | 04 ¦ Cut Over | Restore final log on SQLDB3 | Restore final log sequence on intended primary and recover only at planned point. | DBA Team | Cutover | SQLDB3 online and validated | Not Started | Critical
MIG-038 | 04 ¦ Cut Over | Prepare SQLDB4 for AG join | Restore required logs with NORECOVERY; confirm secondary is ready for AG join. | DBA Team | Cutover | Secondary remains RESTORING; sequence correct | Not Started | Critical
MIG-039 | 04 ¦ Cut Over | Join database to destination AG | Add database on primary and join secondary using approved procedure; validate synchronization. | DBA Team | Cutover | AG database health acceptable | Not Started | Critical
MIG-040 | 04 ¦ Cut Over | Validate listener connectivity | Confirm listener DNS, port, load balancer and app connection path to current primary. | DBA / Network | Cutover | Connection evidence captured | Not Started | High
MIG-041 | 04 ¦ Cut Over | Application smoke tests | Run critical transactions, read/write checks, integrations, jobs and data consistency checks. | App / QC / DBA | Cutover | Acceptance criteria passed | Not Started | Critical
MIG-042 | 04 ¦ Cut Over | Formal GO / NO-GO | Review health, app results, timing, open issues and rollback decision deadline. | Change Lead | Cutover | Decision and timestamp recorded | Not Started | Critical
MIG-043 | 04 ¦ Cut Over | DNS / connection routing | Apply approved DNS/routing changes where required; account for TTL and connection pooling. | Network / App | After go decision | New route confirmed | Not Started | High
MIG-044 | 04 ¦ Cut Over | Rollback and target-write plan | Define source recovery and treatment of any writes accepted on target after cutover. | DBA Lead / App Owner | Before go-live | Rollback is actionable; data-loss impact accepted | Not Started | Critical
MIG-045 | 05 ¦ Stabilize | Enable Query Store | Configure Query Store capture/retention; confirm query, plan and runtime data collection. | DBA Team | Post-cutover | Settings verified | Not Started | High
MIG-046 | 05 ¦ Stabilize | Update statistics | Run approved statistics maintenance; monitor for regressions and resource impact. | DBA Team | Post-cutover | Job completed; performance reviewed | Not Started | High
MIG-047 | 05 ¦ Stabilize | Post-migration baseline | Capture waits, file latency, CPU/memory, PLE and query performance; compare with baseline. | DBA / Monitoring | First 24–72 hours | Comparison reviewed | Not Started | High
MIG-048 | 05 ¦ Stabilize | Compatibility-level decision | Keep tested level initially if appropriate; move to 170 only through controlled validation. | DBA Lead / App | After stabilization | Change separately approved and tested | Not Started | High
MIG-049 | 05 ¦ Stabilize | Validate SQL Agent jobs | Enable approved jobs in order; confirm schedules, owners, proxies and history. | DBA Team | Post-cutover | Required jobs pass test runs | Not Started | High
MIG-050 | 05 ¦ Stabilize | Validate Database Mail & alerts | Test backup, AG health, capacity and operational alerts; verify delivery. | DBA / Monitoring | Post-cutover | Alerts reach support team | Not Started | High
MIG-051 | 05 ¦ Stabilize | Fresh full and log backups | Take a fresh full backup; verify subsequent log backups and recovery requirements. | DBA Team | Post-cutover | Recovery posture verified | Not Started | Critical
MIG-052 | 05 ¦ Stabilize | Monitoring and hypercare | Monitor workload, errors, waits, storage, job failures, AG health and business transactions. | DBA / App / Monitoring | First 3–7 days | No unresolved critical issues; handover accepted | Not Started | High
MIG-053 | 05 ¦ Stabilize | Close change & document lessons | Document final config, known issues, support ownership, runbooks and lessons learned. | Change Lead / DBA Lead | After hypercare | Operations acceptance and change closure | Not Started | Medium
Note on J1: Enter planned date. Overdue incomplete items are highlighted.
Note on L1: Record evidence, ticket number or concise notes. Do not store secrets.

## Risk Register
Risk ID | Risk / Failure Scenario | Impact | Likelihood | Severity | Mitigation / Control | Owner | Trigger / Warning Sign | Contingency / Decision | Status
R-01 | Application incompatibility or changed behavior | High | Medium | High | Run upgrade assessment and representative app/workload tests; obtain app/QC sign-off. | DBA / App Owner | Critical workflow fails or unexpected errors | Stop cutover or follow approved rollback/data plan. | Open
R-02 | Performance regression after engine/compatibility change | High | Medium | High | Capture baseline; test Query Store and compatibility level; approve changes separately. | DBA Lead | Query duration, CPU or latency materially worsens | Apply approved mitigation; defer compatibility change if appropriate. | Open
R-03 | Log shipping lag or missing log backup | High | Medium | High | Monitor backup/restore history and lag; preserve required logs; test alert delivery. | DBA Team | Restore fails or lag exceeds threshold | Resolve sequence before cutover; postpone if readiness criteria fail. | Open
R-04 | Wrong restore sequence or mismatched backup set | High | Low | High | Compare matching backup/restore records; rehearse sequence and validate database state. | DBA Lead | Restore failure or unexpected sequence | Stop; do not recover/join until corrected. | Open
R-05 | Rollback unclear after target accepts writes | High | Medium | Critical | Define source recovery, target-write handling, reconciliation/data-loss approval and deadline. | Change Lead / DBA Lead | NO-GO after target accepted writes | Follow approved recovery and reconciliation plan; do not simply flip DNS. | Open
R-06 | AG listener / load balancer connectivity issue | High | Medium | High | Test DNS, probe, ports, listener and failover from app subnets. | Network / DBA | Connection timeout or wrong replica reached | Use approved network remediation or rollback criteria. | Open
R-07 | Missing login, job or integration dependency | Medium | Medium | High | Inventory metadata; distinguish instance-level and Contained AG objects; test access/jobs. | DBA Team | Login, job or integration failure | Fix under change control; assess go/no-go impact. | Open
R-08 | Insufficient storage or throughput | High | Low | High | Size from workload measurements; validate capacity, latency and growth headroom. | Infra / DBA | Low free space or high file latency | Resize via approved process or postpone cutover. | Open
R-09 | DNS caching / connection pool delays | Medium | Medium | Medium | Review TTL, listener, connection retry and app pool behavior. | Network / App | Clients continue reaching old endpoint | Drain/recycle connections as approved and validate app hosts. | Open
R-10 | Backups or alerting fail after cutover | High | Low | High | Validate fresh full/log backups, Database Mail, ownership, alerts and recovery procedure. | DBA Team | Backup failure or missing notification | Escalate and remediate before operational handover. | Open

## Cutover Runbook
Step | Gate / Activity | Action / Validation | Responsible Role | Expected Result / Evidence | Status | Timestamp | Decision / Notes
C-01 | Readiness & approvals | Confirm change approval, outage window, contacts, tested runbook, recovery posture and rollback deadline. | Change Lead | Approvals recorded. | Not Started
C-02 | Destination readiness | Confirm SQLDB3/SQLDB4, AG/listener/cluster, capacity and monitoring health. | DBA / Infra | Destination passes readiness checks. | Not Started
C-03 | Log shipping readiness | Confirm required logs restored in sequence on both targets; check job history and lag. | DBA | No unexplained gap; restore sequence verified. | Not Started
C-04 | Application freeze | Stop writes/background writers and confirm no sessions/jobs can modify source. | App Owner / DBA | Write freeze confirmed. | Not Started
C-05 | Source AG action | Remove source database from AG only per approved runbook and prerequisites. | DBA Lead | Source AG state recorded. | Not Started
C-06 | Tail-log backup | Take tail-log backup WITH NORECOVERY; verify completion and accessibility. | DBA | Source intentionally left RESTORING. | Not Started
C-07 | Final restore sequence | Restore logs in correct sequence; recover SQLDB3 only at planned recovery point. | DBA | SQLDB3 online; SQLDB4 remains NORECOVERY. | Not Started
C-08 | Destination AG join | Add database on primary and join secondary using approved procedure. | DBA | Synchronization state/health acceptable. | Not Started
C-09 | Connectivity validation | Validate listener, DNS, port/load balancer and app-subnet connectivity. | DBA / Network | Application path reaches intended primary. | Not Started
C-10 | Smoke tests | Test critical transactions, integrations, jobs and data consistency. | App / QC / DBA | Acceptance criteria passed. | Not Started
C-11 | Formal GO / NO-GO | Review health, app sign-off, elapsed time, open issues and rollback consequences. | Change Lead | Decision and approver recorded. | Not Started
C-12 | Routing change | Apply approved DNS/routing changes; account for TTL and pooled connections. | Network / App | New route verified from app hosts. | Not Started
C-13 | Post-cutover backup | Run a fresh full backup and confirm subsequent log backups and alert delivery. | DBA | Recovery posture verified. | Not Started
C-14 | Hypercare | Start enhanced monitoring, incident tracking and stakeholder updates. | DBA / App / Monitoring | Owner and duration agreed. | Not Started

## Test & Validation
Test ID | Category | Test Scenario | Execution / Evidence | Expected Outcome | Owner | Result | Severity if Failed | Defect / Evidence Link | Retest Result
T-01 | Infrastructure | Windows cluster validation | Attach validation report | No unresolved blocking validation issue. | Not Run | High |  | Not Run
T-02 | HA / AG | Planned AG failover | Record failover time and app behavior | Target replica becomes primary and app reconnects as designed. | Not Run | High |  | Not Run
T-03 | HA / AG | Controlled node interruption | Record failover/recovery observations | Failover matches approved design. | Not Run | High |  | Not Run
T-04 | Connectivity | Listener from app subnet | Record DNS, port and connection result | Connection reaches current primary. | Not Run | High |  | Not Run
T-05 | Database | Database integrity | Run approved DBCC CHECKDB strategy; record result | Integrity checks meet acceptance criteria. | Not Run | High |  | Not Run
T-06 | Migration | Log backup/restore sequence | Capture matching backup/restore history and LSN evidence | Required logs restored in order with no unexplained gap. | Not Run | High |  | Not Run
T-07 | Security | Login and permission validation | Test representative app/support identities | Required access works; unauthorized access remains denied. | Not Run | High |  | Not Run
T-08 | Application | Critical business transaction | Execute approved smoke-test scenario | Transaction completes and data is correct. | Not Run | High |  | Not Run
T-09 | Integration | Linked server / ETL / external integration | Run representative end-to-end test | Integration succeeds with expected data flow. | Not Run | High |  | Not Run
T-10 | Jobs | SQL Agent job validation | Execute selected jobs and inspect history | Required jobs run under correct owner/proxy and schedule. | Not Run | High |  | Not Run
T-11 | Monitoring | Alert delivery test | Trigger safe test alert; validate recipient | DBA team receives actionable notification. | Not Run | High |  | Not Run
T-12 | Backup | Fresh full/log backup validation | Record job result/location; restore-test per policy | Backups complete and recovery chain meets policy. | Not Run | High |  | Not Run
T-13 | Performance | Baseline comparison | Compare query duration, waits, CPU and I/O | Within agreed thresholds or mitigations approved. | Not Run | High |  | Not Run
T-14 | Recovery | Rollback tabletop / rehearsal | Record source recovery and target-write handling | Rollback plan is executable and decision points clear. | Not Run | High |  | Not Run

## Decision Log
Decision ID | Date | Decision / Topic | Options Considered | Decision & Rationale | Approver | Impact / Dependencies | Follow-up Owner | Due Date | Status
D-001 | [8 empty] | Open
D-002 | [8 empty] | Open
D-003 | [8 empty] | Open
D-004 | [8 empty] | Open
D-005 | [8 empty] | Open
D-006 | [8 empty] | Open
D-007 | [8 empty] | Open
D-008 | [8 empty] | Open
D-009 | [8 empty] | Open
D-010 | [8 empty] | Open

## Read Me
FIELD GUIDE ¦ SQL SERVER MIGRATION PLAYBOOK
A practical companion to the SQL Server 2016 → 2025 two-part article series
PURPOSE
A reusable planning and execution workbook for a side-by-side SQL Server upgrade. Covers assessment, destination build, log shipping preparation, cutover control, validation, risk management and stabilization.
WORKBOOK TABS
Migration Command Center — high-level phase view and status KPIs. Master Checklist — actionable tasks, owners, dates, status, priority and evidence. Risk Register — risks, controls, warning signs and contingency actions. Cutover Runbook — ordered cutover gates and execution evidence. Test & Validation — infrastructure, HA, application, backup, monitoring and rollback tests. Decision Log — decisions, approvers, rationale and follow-up.
RECOMMENDED WORKFLOW
1. Save a project-specific copy. 2. Replace example server names and assumptions. 3. Assign accountable owners and target dates. 4. Define pass/fail thresholds and evidence locations. 5. Rehearse migration and rollback before production. 6. Update checklist/runbook status during execution. 7. Store approved change records and evidence in your organization's system.
IMPORTANT TECHNICAL GUARDRAILS
• Multiple log backup jobs do not inherently break the log chain. Coordinate schedules, destinations, retention and cleanup, and verify required logs restore in sequence. • Compare matching backup/restore records; independently selecting each latest LSN may compare different backup sets. • Tail-log backup WITH NORECOVERY leaves the source database in RESTORING. Rollback must define source recovery and handling of writes accepted on target. • Follow a tested, supported restore/AG join sequence for your SQL Server version and Contained AG design. • Compatibility level 130 vs 170 is workload-specific; test and approve changes separately. • Validate SQL Server 2025, Windows Server, Azure networking, licensing and feature support against current documentation and the exact build.
PUBLICATION NOTE
Educational planning template only. Example server names, timings, owners and thresholds must be adapted. It does not replace an approved change plan, backup validation, security review or tested rollback.